## README
A8 - Risk Register
Team Name | Dunder Mifflin IT Company
Team Member Names | Anita Hu Kavit Mehta Muhammed Aflah Ziyue Li
Date | 2024-10-31
Project Summary | The purpose of this project is to make Starship robots’ food deliveries on the UW-Madison campus more efficient so that customers receive their order fresh and in a timely manner. By optimizing delivery paths, improving app functionality, and designing better food freshness techniques, we aim to enhance the overall customer experience. This project’s ultimate goal is to increase customer satisfaction, reduce delivery-related complaints, and contribute to higher customer acquisition/retention as well as reduced operational costs. Since it’s an official UW-Madison partnered food delivery service, we want the Starship system to adhere to the university’s gold standards in making student life easier and more accessible.

## risk_register
Significance Scale
0-5
2024-06-10
2024-11-15
16-20
21-25
Risk ID | Risk Name | Date Identified | Condition | Consequence | Probability | Severity | Significance | Response Strategy | Response Details
1 | Robot Malfunction | 2024-10-30 | If a delivery robot malfunctions during an active delivery... | Then the order may be delayed, resulting in customer dissatisfaction and potential loss of customers. | 2 | 4 | 8 | Mitigate | Regular maintenance checks on delivery robots and immediate backup protocols in case of robot malfunction.
2 | Vendor Notification System Failure | 2024-10-30 | If the vendor notification system fails to alert vendors about new orders in a timely manner... | Then orders may not be fulfilled on time, leading to customer complaints and a loss of trust in the service. | 2.5 | 5 | 12.5 | Contingency Plan | Establish a backup notification channel (e.g., SMS or email) to alert vendors if the primary system fails.
3 | Cold Weather Impact | 2024-10-30 | If extremely cold weather affects the robot’s performance and battery life... | Then deliveries may be delayed or halted, impacting customer satisfaction and system reliability. | 1 | 5 | 5 | Contingency Plan | Implement a manual delivery option or assign designated personnel to assist with deliveries during extreme weather conditions.
4 | Price Discrepancy Between App and In-Store | 2024-10-30 | If the prices on the app are higher than in-store prices... | Then customers may feel overcharged, leading to reduced usage of the app. | 4.5 | 3 | 13.5 | Mitigate | Regularly review and adjust app prices to align with in-store prices, and clearly communicate any discrepancies to customers.
5 | Delivery Location Inaccessibility | 2024-10-30 | If the app doesn't allow to pinpoint the exact delivery location on the map... | Then customers may need to travel to get the order at some other delivery location, and also not receive it timely. This will annoy them and Starship will lose customers. | 5 | 3 | 15 | Mitigate | Increased map accuracy and more choice of delivery locations.
6 | Payment Transaction Failure | 2024-10-30 | If the app doesn't process payment transactions and causes failure... | Then customers may cancel the order and tend to use other apps. | 3 | 5 | 15 | Avoid | Increase the stability of the system and add maintenance personnel.
7 | Lack of Food Choices | 2024-10-30 | If there aren't enough options in the app for customers to choose what they want... | Then customers will use other apps with more choices, thus reducing the usage of starship. | 4 | 4 | 16 | Avoid | Cooperate with more vendors to provide more food options to customers.
8 | Failing Insulation System | 2024-10-30 | If the robot's enhanced insulation system malfunctions during deliveries... | Then the food will arrive cold and lead to customer dissatisfaction. | 2 | 3.5 | 7 | Mitigate | Regular maintenance checks on the robot's insulation system.
9 | Snow Induced Delivery Issues | 2024-10-31 | If the robot is unable to access paths affected by snow fall... | Then deliveries may fail, requiring manual intervention and affecting delivery times. | 4 | 3 | 12 | Accept | Snowfall being a natural phenomena affects all businesses in different ways, and customers are largely understanding of this situation. Manual intervention by university/city services helps clear blockage.
10 | Robot Theft or Vandalism | 2024-10-31 | If robots get stolen or vandalized on the streets... | Then deliveries may fail, customers will get dissatisfied, and starship may incur increased expenses for replacement of the lost robot. | 2 | 5 | 10 | Contingency Plan | System to engage law and enforcement and backup robots to replace the stolen ones.
11 | Data Privacy Breach | 2024-10-31 | If customer data from the app or delivery system is compromised... | Then it would lead to loss of customer trust and potential legal consequences. | 1 | 5 | 5 | Avoid | Conduct regular security assessments and penetration testing, implement network segmentation, train staff on security measures.
12 | Competition from Rivals | 2024-10-31 | If a competitor app provides better deals and service... | Then it would lead to loss of customer and market share. | 3 | 3 | 9 | Accept | Continuously work on providing better service, and place customer feedback at the center.